## Sheet1
Teams/Emails | Projects | Status | Time | Deliverables to be presented to Core Team/Community | By what date… | who will have… | accomplished action towards deliverable | with these resources… | to be measured by..
Innovation #1 | Design a county data system to track supply and demand within Behavioral Health Care
| Behavioral Care Analysis Project * | started | 3-6 mo. | one page overview on current status
| Behavioral Care Access Project * | started | 3-6 mo. | one page overview on access
| All-Payer Claims Database | possible | 5-7 mo. | one page overview on county ailments
| Where does the Behavioral Health System exist? (Geo map overlay) * | started | 3 mos. | present findings to Core Team
| Public Transit to care project | possible | 3 mos. | map overlay
Innovation #2 | Ensuring current accessible behaviroal health care programs are fully supported
| Who is working on accessible behavioral health? Project | possible | 3-6 mo. | Summary of financial support needs for programs serving most vulnerable
Innovation #3 | Engaging the private sector in supporting behaviroal health care innovations
| Technology that supports behavioral health project | possible | 1-3 mo. | Summary of tech supports available: see
Innovation #4 | Harnessing technology to create an online directory and resources
| Plain language on existing websites project | possible | 3-6 mo. | Summary of research on how well local websites direct to services
Innovation #5 | Generating public awareness and engagement
| Create a Behavioral Health @100% user friendly website | started | 3-6 mo. | Research what works, find experts to guide implementation
| Be patient and focused (Align with other groups on same topic) | possible | 4 months | Attend at least a quarter's worth of othe community meetings.
| Address mental illness stigma and normalize behavioral health | started | 3-6 mo. | Summary of who could implement at ongoing county-wide campaing
| Address substance use disorders stigma and normalize treatment | possible | 3 mo. | Summary of who could implement at ongoing county-wide campaing
| Email Behavioral Health @100% stakeholders often | started | 4 months | Indentify most tech saavy person, create county-wide list, create info-graphic and messages, test, tweak and implement
Innovation #6 | Make sure education system is on board
| Explore Santa Fe "Sky Center" model | possible | 1-2 mo. | Connect with staff, research structure and delivery, summary finding on one pager
| Can Madison Public Schools model work for us? Project | possible | 1 mo. | Connect with staff, research structure and delivery, summary finding on one pager
| Breaking the Silence Model for educator education | possible | 3-6 mo. | Connect with staff and provide education on depression generally and risk factors for unintended pregnancies
| Analyze rural Kentucky online care model | possible | 1 mo. | Connect with staff, research structure and delivery, summary finding on one pager
Innovation #7 | Ensuring that local higher education is engaged in solutions, research and eval
| Convene beh health providers training programs to address provider scarcity | started | 3-6 mo. | explore state's higher ed programs and find out who is offering incentives to go into counseling, what is future capapcity, and develop one page brief
| Learn how Oregon does incentives project | possible | 1 mo. | research Oregon's model for incentive and provide one-page summary
| "Emotional Care for U" project | possible | 1 mo. | Research Eastern NM's campus based care and see if this could be funded, impleted here at UNM-VC
| ECHO and Telemed for provider mentoring project | started | 1-3 mo.
| Evaluate effectiveness of Mental Health First Aid - do we have servies to refer to prior to training taking place? | complete | 1 mo. | Our county has enough services to make MHFA an effective strategy beyond raising awareness and reducing stigma - Diana Good can show this.
| Integrate ACE's data and Resilient Communities Survey data into Primary care | possible | 1-3 years | Connect with local clinic and see if they could use these two surveys as part of screening patients.
| Evaluate the Mental Health & Psychological Support model | possible | 1-3 mo. | Explore website mhpss.net, connect with staff and create summary of user's infor inf available.
| Find ground-breaking approaches to substance use. | possible | 1-3 mo. | Convene higher ed and public health to explore policy changes. Summarize results of conveneing in page including any recommendations.
Innovation #8 | Support city and county gov. in behavioral health innovation
| Learn how other municipalities address behavioral health | possible | 3-6 mo. | create one page summary on research findings.
Innovation #9 | Indentify how the federal govt. and state can strengthen local services
| Invest wisely in care for all | possible | 3 mos. | Discover all sources of foundation funding to support beh health. Develop one pager of results.
| State Coaltition to make things happen | possible | 3-6 mo. | Conduct key informant interviews of change makers. Assess the data driven qualities of current coalition. Create one paper of results
Innovation #10 | Create a County or City Dept. of Behavioral Health that is funded.
| County/City partnership that funded the Dept | possible
| Co-train advocates on how to get to law-makers | possible | 3 mos. | Find local public speaking expert and create workshop for community to be able to speak effectively on needs for behavioral health.
| Know your stiff before you meet the mayor project | possible | 3 mos. | Research all innovations before approaching leaders.
| Create a bold vision and strategic plan | possible | 3-6 mos. | After Inn. #1 and survey of Task Force Members, create strat plan.